## Sprint Backlog
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
As a user I want to see prices. As a user I want insurace that I won't be lobotomized. As a user I want absolute confidentiality. | Create F.A.Q. template. | Adam | Completed | 3 | 1 | 1 | 1 | 0 | 2
| Populate with questions and answers. | Adam | Completed | 3 | 1 | 1 | 1 | 0 | 2
| Convert to XML. | Levi | In Progress | 7 | 0 | 0 | 0 | 0 | 0
As a customer I want to see prices up front for comarison | Create EgoTrip description. | Andrew | Completed | 4 | 1 | 1 | 1 | 1 | 1
| Create EgoTrip customization options. | Andrew | Completed | 2 | 0 | 7 | 0 | 0 | 1
| Convert to XML. | Levi | In Progress | 7 | 2 | 2 | 2 | 1 | 0
| Use JavaScript to import to web page. | Everyone | In Progress | 7 | 2 | 2 | 2 | 1 | 0
| Total |  |  | 33 | 7 | 14 | 7 | 3 | 6

## Product Backlog
Story_Nbr | User_Story_Description | Acceptance_Criteria | Story_Points | Priority
US-01 | As a customer I want to see prices up front for comarison | 1. Website and mobile app will allow side by side comparison with full layout of package details. 2. Will be able to sort by new arrivals, relevance, price, and avg. rating. | 3 | 1
US-02 | As a customer I want to choose the location the implant takes place in. | 1. Previews, testemonials, screenings, and interviews from former clients | 5 | 2
US-03 | As a customer I want to schedule implants online. | 1. website and mobile app will have interactive calendar to schedule appointments. | 2 | 1
US-04 | As a customer I want to see video examples of other memory implants. | 1. Advertising and highlight reel of trips from others. | 8 | 2
US-05 | As a customer I want to include real people in my implants | 1. Request permsion from other parties for likeness. 2. Memory scans for personality derivatve | 144 | 1
US-06 | As a customer I want to role play a character of my choice in my implant | 1. Informative material on each role describing their background, attitude, and special skills. All of which will be interchangable. | 34 | 1
US-07 | As a customer I want to see the most popular packages | 1. Record metrics of our customers choices. | 21 | 2
US-08 | As a customer I want to see a mock up of my custom implant | 1. After deposit is received, use will have one last chance to review and finalize their role and destination before implanting memory. | 13 | 1
US-09 | As a customer I want to be able to choose a group implant with friends. | 1. Offer group packages for 2 or more. | 21 | 2
US-10 | As a customer I want videos, photos and other mementos from my implant. | 1. During post implant screening, user will be able to look through his memory and choose his clips and videos he wishes to take home. | 8 | 3
US-11 | As a customer I want insurance that I will not be lobotomized, memory wiped and/or dumped into an alley way out of a Johnny Cab TM. | 1. Implant insurance. | 21 | 3
US-12 | As a customer I want absolute confidentiality of my implants. | 1. Strict doctor patient confidentiality clause. | 2 | 2
US-13 | As a customer I want celebrities in my implants. | 1. Will offer cameos for those who wish to have celebrities in their implants. | 55 | 2
Fibonacci Series: 1,2,3,5,8,13,21,34,55,89,144,233